## Sheet1
Group Contribution log SOEN341 project
Names and ID: Colin Haller (40278545), Gabriel Gallant (40328473), Lizzie Nicole Gudiño Cabrera (40272383), Brice Bryan Iteka (40246704), Hirdayraj Singh Nanda (40305593) |  |  |  | , Moaiad Akari (40328240)
First Name | Last Name | Nickname | GitHub Username
Lizzie Nicole | Gudiño Cabrera | Lizzie | lizziengc
Brice Bryan | Iteka | Bryan | Bryanoff
Moaiad | Akari | Moaiad | MoaiadAkari
Gabriel | Gallant | Gabe | gabrielgallant
Colin | Haller | Colin | C4ller
Hirdayraj | Nanda | Hirday | Hirdayraj
Activity Table |  |  |  | Sprint 1: Hours Spent on Assigned Tasks
Date | Activity Type |  |  | Bryan | Lizzie | Moaiad | Hirdrayaj | Colin | Gabriel
2026-01-23 | Group Meeting #1 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
2026-01-24 | Lizzie created the Spint planning, came up with different US and drew the sketches for the wireframe |  |  |  | 3.5
2026-01-25 | Group Meeting #2 |  |  | 1 | 1 | 1 | 1 | 1 | 1
2026-01-30 | Colin Researched DataBase Solutions | [6 empty] | 1
2026-01-30 | Group Meeting #3 |  |  | 2 | 2 | 2 | 2 | 2 | 2
2026-01-31 | Gabriel created wireframe in UXPin and added pages: login, registration, meal plan + learning html, css and js | [7 empty] | 8.5
2026-01-31 | Colin set up the frontend environment | [6 empty] | 1
2026-01-31 | Bryan researched and got familiar with backend framework (spring boot, gradle) |  |  | 3
2026-02-01 | Gabriel added profile display, profile editing, recipes and reset password page to UXPin | [7 empty] | 2
2026-02-01 | Colin set up the rest of the environment | [6 empty] | 4
2026-02-01 | Moaiad made a registration page (was discarded later) |  |  |  |  | 5
2026-02-02 | Gabriel coded homepage/meal plan page | [7 empty] | 2.25
2026-02-02 | Lizzie created the sign up, reset password and create account website with js, html and css (issue #1) |  |  |  | 7
2026-02-03 | Colin completed his tasks and helped Bryan with environment setup | [6 empty] | 2.5
2026-02-03 | Bryan completed his task (User story 4) |  |  | 5
2026-02-03 | Hirday completed his task for veryfying matching passwords and saving username and password in database during signup & (issue #2) | [5 empty] | 3.5
2026-02-03 | Group Meeting #4 |  |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 0.25
2026-02-04 | Hirday completed the task (with Colin) for having the option to reset the password with email (Issue #1) | [5 empty] | 4
2026-02-04 | Moaiad made a user profile page that have the dietary information |  |  |  |  | 6
2026-02-04 | Lizzie and Moaiad discussed frontend linking styles
2026-02-04 | Colin reviewed backend/ frontend linking with Lizzie |  |  |  | 0.5 |  |  | 0.5
2026-02-04 & 2026-02-05 | Lizzie made the reset password page connected it to the link, added fetch functions to the sign up and login page, created the user information page |  |  |  | 7.5
2026-02-05 | Bryan reworked/updated user story 4 tasks to include all the user data and should be able to store multiple choices for each type of data |  |  | 5
2025-02-05 | Colin, Bryan and Hyrdrayaj had a meeting about merging the backend and testing the app |  |  | 2.5 |  |  | 2.5 | 2.5
2025-02-06 | Lizzie and Colin fixed the bugs between frontend/backend |  |  |  | 3.5 |  |  | 4
Total Hours |  |  |  | 20.25 | 26.75 | 15.75 | 14.75 | 20.25 | 16.5