## Cover Page
Canadian Coders
Prepared By:
Hirdayraj Singh Nanda 40305593
Moaiad Akari 40328240
Colin Haller 40278545
Gabriel Gallant 40328473
Lizzie Nicole Gudino cabrera 40272383
Brice Bryan Iteka 40246704

## Product Backlog
Issue # | User story | Associated Tasks | Story points associated to a US | Priority | Risk (High, Medium, Low) | Responsible | Due date
1 | Once website is clicked, user will see the login page | -Create UI for a login page or sign up page (email, password) (FE) -Create an option for the user to reset the password with the email - Verify that the login email and password are the same as in the database | 5 | HIGH | MEDIUM | Front End: Lizzie & Bryan Back End: Colin & Hirdayraj | February 4th,2026 | US for Sprint 1
2 | User's information is saved during signup | -Verify that the 2 password inputs match in case of login (BE) -Create a function that saves user name and password in the database during signup - Create a table in the database | 2 | MEDIUM | LOW | Back End: Hirdayraj | February 4th,2026
3 | Once signup is done and saved, user will see registration page | -Create UI for create account (first & last name, age, sex, ) -Create a following page to select different options from a checklist for diet & allergies | 4 | MEDIUM | MEDIUM | Front End: Moaiad & Gabriel | February 4th,2026
4 | User's profile information is saved | -Create a function that saves user data in the database during signup | 2 | MEDIUM | LOW | Back End: Bryan | February 4th,2026
5 | User has a nice interface for the homepage. Acceptance criteria: The main features shall be accessable using buttons where the response time for switching pages is within 100 milliseconds. | -Create digital wireframe of the homepage layout -Add main features like the heading, the different options (meal plan/calendar, groceries, recipes), add the profile button and others | 5 | LOW | MEDIUM | Front End: Gabriel | February 4th,2026
6 | User can access a meal planner page | - Add intial layout with calendar and meal plan - Add a calendar with current dates and days of the week - Add function to add a meal which includes meal type, recipes, etc - Add function to delete and edit meal - Add button to plan a meal plan where you can choose from the available recipes - Add a function in meal plan that eliminates the recipe from the available recipes once chosen in the plan |  | HIGH | HIGH | Front End: Gabriel
7 | User can access the recipes page | - Add an inital layout with my recipes - Add function to create, edit and delete recipe -Add list to choose difficulty for recipe - Add function to search ingredients and dietary tag - Add box to insert prep steps and time and cost - Add search bar to search recipes -Add function to filter recipes based on Time, difficulty, cost, dietary tag, etc. |  | MEDIUM
8 | User can acess the groceries page | - Add a function that lists all major groceries in the area - Add a search bar for product and lists form all the groceries selected the cheapest prices to the most expensive - Add function to create and edit a checklist for groceries -Add a list of favourite food -Using data from checklist groceries & favourite food, display favourites if sale |  | MEDIUM
9 | User will benefit from an enhanced user interface
10
|  | Total: | 18